## ALL
James Hargreaves Hall 3 year Development Plan Last Updated: 15.10.17
| 2016 |  |  |  |  | 2017 |  |  |  | 2018
|  | Activity | Responsible group/person | Completed |  |  | Activity | Responsible group/person | Completed |  | Activity | Responsible group/person | Completed
General Maintenance | Exterior | Re-Paint shed | Karen Southcott | Completed May 2016 | General | Exterior | Maintenance of Arch Window Management of Condensation Issue | Hall Committee | Ongoing | Exterior | Review Exterior Refurbishment needs | Hall Committee | Discuss Jan 2018
|  | Order & Lay New Gravel for Parking Area & Maintenance of Graveyard | Karen Southcott Judy Godfrey Phyllis Diment | Completed Aug 2016 |  |  | Maintain Gravel Parking Area & Maintenance of Graveyard | Karen Southcott Judy Godfrey Phyllis Diment | Ongoing |  | Maintain Gravel Parking Area & Maintenance of Graveyard | Karen Southcott Judy Godfrey Phyllis Diment | Ongoing
| Interior | Floor Maintenance: Sanded & Polished Every 2 years | Cleaning Team Judy Godfrey | Completed Aug 2015 | Maintenance | Interior | Floor Maintenance: requires sanding & polishing this year | Cleaning Team Judy Godfrey | Completed Aug 2017 | Interior | Floor Maintenance: Carried out as part of cleaning rota | Cleaning Team Judy Godfrey | Ongoing
Building works | Exterior | Remedial work to Rear Steps and Boundary Wall | Hall Committee | Completed Aug 2015 | Building works | Exterior | Review Exterior Paintwork, repaint posts and fence | Hall Committee | Completed Aug 2017 | Exterior
| Interior | Review Interior Paint Renovations | Hall Committee | Reviewed July 2016 |  | Interior | Review Interior Paint Renovations Paint Renovations to the toilet | Hall Committee Karen Southcott | Completed Aug 2017 | Interior | Review Interior Paint Renovations | Hall Committee | Due Aug 2019
Health & Safety |  | Review storage Requirements & Tidy Loft | Hall Committee | Completed Aug 2015 | Health & |  | Review storage Requirements | Hall Committee | Due Nov 2017 |  | Review storage Requirements | Hall Committee | Ongoing
|  | Carry out annual H&S risk assessments | Karen Southcott | Completed Nov 2016 | Safety |  | Carry out annual H&S risk assessments | Karen Southcott | Completed Oct 2017 |  | Carry out annual risk assessments, including disability | Hall Committee | Due Oct 2018
|  | Annual Fire Risk Assessment | Karen Southcott | Completed Oct 2016 |  | Health & Safety | Annual Fire Risk Assessment | Karen Southcott | Completed Oct 2017 | Health & Safety | Annual Fire Risk Assessment | Karen Southcott | Due Oct 2018
|  | Ensure electrical tests are carried out - due in 2 years time | Judy Godfrey | Completed Oct 2015 |  |  | Ensure electrical tests are carried out-due Oct 2017 | Judy Godfrey | Due Oct 2017 |  | Ensure annual electrical tests are carried out | Judy Godfrey | Due Oct 2018
Support for disabled |  | Review Disability Access Risk Assessment/Questionnaire | Karen Southcott | Completed Oct 2016 | Support for disabled | Support for disabled | Annual evaluation of disability access risks | Karen Southcott | Completed Oct 2017 | Support for disabled | Annual evaluation of disability access risks | Karen Southcott | Due Oct 2018
User groups |  | Review user groups . Build up profile of coverage and attendance. Survey/questionaire to ascertain needs | Hall Committee | Ongoing | User groups | User groups | Review user groups . Build up profile of coverage and attendance. Survey/questionaire to ascertain needs | Hall Committee | Ongoing | User Groups | Use information to target future use. | Hall Committee | Ongoing
Committee |  | Review committee Structure. Produce Committee Responsibility List | Hall Committee | Revised Nov 2016 | Committee |  | Review committee Structure. Review Hall Governing Body Document | Hall Committee | Due Nov 2017 |  | Continue to review committee requirements & recruitment when necessary. | Hall Committee | Due Feb 2018
|  | Maintain & Improve Hall Website | Karen Southcott | Ongoing |  | Committee | Maintain & Improve Hall Website | Karen Southcott | Ongoing | Committee | Maintain & Improve Hall Website | Karen Southcott | Ongoing
|  | Review "Mission" & "Value Add" Statements. Are they still valid? | Hall Committee | Reviewed Nov 2016 |  |  | Review "Mission" & "Value Add" Statements. Are they still valid? | Hall Committee | Due Nov 2017 |  | Review "Mission" & "Value Add" Statements. Are they still valid? | Hall Committee | Due Nov 2018
|  | Distribute Welcome Pack for people moving to the village | Judy Godfrey | Ongoing |  |  | Distribute Welcome Pack for people moving to the village | Judy Godfrey | Ongoing |  | Distribute Welcome Pack for people moving to the village | Judy Godfrey | Ongoing
Events | Community Activities/ Support | Review hall hiring documentation. Review range of activities & ages. Discuss gaps & how to fill them. | Hall Committee | Ongoing | Events | Community Activities/ Support | Review hall hiring documentation. Review range of activities & ages. Discuss gaps & how to fill them. | Hall Committee | Ongoing | Community Activities/ Support | Review & Revise Welcome Pack for new arrivals when necessary. Review activities, frequency & ages of clubs/events | Hall Committee | Ongoing
| Fund Raising | Review fund raising activities for year and implement changes. | Hall Committee | Ongoing at Committee Meetings |  | Fund Raising | Review fund raising activities for year and implement changes. | Hall Committee | Ongoing | Fund Raising | Develop new events in order to raise funds | Hall Committee | Ongoing at Committee Meetings
Finance |  | Breakdown of income & expenditure. Presented at monthly committee mtgs | Judy Godfrey | Monthly Report Produced | Finance | Finance | Breakdown of income & expenditure. Presented at monthly committee mtgs | Judy Godfrey | Monthly Report Produced | Finance | Breakdown of income & expenditure. Presented at monthly committee mtgs | Hall Committee | Monthly Report Produced

## 2016-17
James Hargreaves Hall 3 year Development Plan Last Updated: 15.10.17
| 2016 |  |  |  |  | 2017
|  | Activity | Responsible group/person | Completed |  |  | Activity | Responsible group/person | Completed
General Maintenance | Exterior | Re-Paint shed | Karen Southcott | Completed May 2016 | General | Exterior | Maintenance of Arch Window Management of Condensation Issue | Hall Committee | Ongoing
|  | Order & Lay New Gravel for Parking Area & Maintenance of Graveyard | Karen Southcott Judy Godfrey Phyllis Diment | Completed Aug 2016 |  |  | Maintain Gravel Parking Area & Maintenance of Graveyard | Karen Southcott Judy Godfrey Phyllis Diment | Ongoing
| Interior | Floor Maintenance: Sanded & Polished Every 2 years | Cleaning Team Judy Godfrey | Completed Aug 2015 | Maintenance | Interior | Floor Maintenance: requires sanding & polishing this year | Cleaning Team Judy Godfrey | Completed Aug 2017
Building works | Exterior | Remedial work to Rear Steps and Boundary Wall | Hall Committee | Completed Aug 2015 | Building works | Exterior | Review Exterior Paintwork, repaint posts and fence | Hall Committee | Completed Aug 2017
| Interior | Review Interior Paint Renovations | Hall Committee | Reviewed July 2016 |  | Interior | Review Interior Paint Renovations Paint Renovations to the toilet | Hall Committee Karen Southcott | Completed Aug 2017
Health & Safety |  | Review storage Requirements & Tidy Loft | Hall Committee | Completed Aug 2015 | Health & |  | Review storage Requirements | Hall Committee | Due Nov 2017
|  | Carry out annual H&S risk assessments | Karen Southcott | Completed Nov 2016 | Safety |  | Carry out annual H&S risk assessments | Karen Southcott | Completed Oct 2017
|  | Annual Fire Risk Assessment | Karen Southcott | Completed Oct 2016 |  | Health & Safety | Annual Fire Risk Assessment | Karen Southcott | Completed Oct 2017
|  | Ensure electrical tests are carried out - due in 2 years time | Judy Godfrey | Completed Oct 2015 |  |  | Ensure electrical tests are carried out-due Oct 2017 | Judy Godfrey | Due Oct 2017
Support for disabled |  | Review Disability Access Risk Assessment/Questionnaire | Karen Southcott | Completed Oct 2016 | Support for disabled | Support for disabled | Annual evaluation of disability access risks | Karen Southcott | Completed Oct 2017
User groups |  | Review user groups . Build up profile of coverage and attendance. Survey/questionaire to ascertain needs | Hall Committee | Ongoing | User groups | User groups | Review user groups . Build up profile of coverage and attendance. Survey/questionaire to ascertain needs | Hall Committee | Ongoing
Committee |  | Review committee Structure. Produce Committee Responsibility List | Hall Committee | Revised Nov 2016 | Committee |  | Review committee Structure. Review Hall Governing Body Document | Hall Committee | Due Nov 2017
|  | Maintain & Improve Hall Website | Karen Southcott | Ongoing |  | Committee | Maintain & Improve Hall Website | Karen Southcott | Ongoing
|  | Review "Mission" & "Value Add" Statements. Are they still valid? | Hall Committee | Reviewed Nov 2016 |  |  | Review "Mission" & "Value Add" Statements. Are they still valid? | Hall Committee | Due Nov 2017
|  | Distribute Welcome Pack for people moving to the village | Judy Godfrey | Ongoing |  |  | Distribute Welcome Pack for people moving to the village | Judy Godfrey | Ongoing
Events | Community Activities/ Support | Review hall hiring documentation. Review range of activities & ages. Discuss gaps & how to fill them. | Hall Committee | Ongoing | Events | Community Activities/ Support | Review hall hiring documentation. Review range of activities & ages. Discuss gaps & how to fill them. | Hall Committee | Ongoing
| Fund Raising | Review fund raising activities for year and implement changes. | Hall Committee | Ongoing at Committee Meetings |  | Fund Raising | Review fund raising activities for year and implement changes. | Hall Committee | Ongoing
Finance |  | Breakdown of income & expenditure. Presented at monthly committee mtgs | Judy Godfrey | Monthly Report Produced | Finance | Finance | Breakdown of income & expenditure. Presented at monthly committee mtgs | Judy Godfrey | Monthly Report Produced

## 2017-18
James Hargreaves Hall 3 year Development Plan Last Updated: 15.10.17
|  | 2017 |  |  |  | 2018
|  |  | Activity | Responsible group/person | Completed |  | Activity | Responsible group/person | Completed
General Maintenance | General | Exterior | Maintenance of Arch Window Management of Condensation Issue | Hall Committee | Ongoing | Exterior | Review Exterior Refurbishment needs | Hall Committee | Discuss Jan 2018
|  |  | Maintain Gravel Parking Area & Maintenance of Graveyard | Karen Southcott Judy Godfrey Phyllis Diment | Ongoing |  | Maintain Gravel Parking Area & Maintenance of Graveyard | Karen Southcott Judy Godfrey Phyllis Diment | Ongoing
| Maintenance | Interior | Floor Maintenance: requires sanding & polishing this year | Cleaning Team Judy Godfrey | Completed Aug 2017 | Interior | Floor Maintenance: Carried out as part of cleaning rota | Cleaning Team Judy Godfrey | Ongoing
Building works | Building works | Exterior | Review Exterior Paintwork, repaint posts and fence | Hall Committee | Completed Aug 2017 | Exterior
|  | Interior | Review Interior Paint Renovations Paint Renovations to the toilet | Hall Committee Karen Southcott | Completed Aug 2017 | Interior | Review Interior Paint Renovations | Hall Committee | Due Aug 2019
Health & Safety | Health & |  | Review storage Requirements | Hall Committee | Due Nov 2017 |  | Review storage Requirements | Hall Committee | Ongoing
| Safety |  | Carry out annual H&S risk assessments | Karen Southcott | Completed Oct 2017 |  | Carry out annual risk assessments, including disability | Karen Southcott | Due Oct 2018
|  | Health & Safety | Annual Fire Risk Assessment | Karen Southcott | Completed Oct 2017 | Health & Safety | Annual Fire Risk Assessment | Karen Southcott | Due Oct 2018
|  |  | Ensure electrical tests are carried out-due Oct 2017 | Judy Godfrey | Due Oct 2017 |  | Ensure annual electrical tests are carried out | Judy Godfrey | Due Oct 2018
Support for disabled | Support for disabled | Support for disabled | Annual evaluation of disability access risks | Karen Southcott | Completed Oct 2017 | Support for disabled | Annual evaluation of disability access risks | Karen Southcott | Due Oct 2018
User groups | User groups | User groups | Review user groups . Build up profile of coverage and attendance. Survey/questionaire to ascertain needs | Hall Committee | Ongoing | User Groups | Use information to target future use. | Hall Committee | Ongoing
Committee | Committee |  | Review committee Structure. Review Hall Governing Body Document | Hall Committee | Due Nov 2017 |  | Continue to review committee requirements & recruitment when necessary. | Hall Committee | Due Feb 2018
|  | Committee | Maintain & Improve Hall Website | Karen Southcott | Ongoing | Committee | Maintain & Improve Hall Website | Karen Southcott | Ongoing
|  |  | Review "Mission" & "Value Add" Statements. Are they still valid? | Hall Committee | Due Nov 2017 |  | Review "Mission" & "Value Add" Statements. Are they still valid? | Hall Committee | Due Nov 2018
|  |  | Distribute Welcome Pack for people moving to the village | Judy Godfrey | Ongoing |  | Distribute Welcome Pack for people moving to the village | Judy Godfrey | Ongoing
Events | Events | Community Activities/ Support | Review hall hiring documentation. Review range of activities & ages. Discuss gaps & how to fill them. | Hall Committee | Ongoing | Community Activities/ Support | Review & Revise Welcome Pack for new arrivals when necessary. Review activities, frequency & ages of clubs/events | Hall Committee | Ongoing
|  | Fund Raising | Review fund raising activities for year and implement changes. | Hall Committee | Ongoing | Fund Raising | Develop new events in order to raise funds | Hall Committee | Ongoing at Committee Meetings
Finance | Finance | Finance | Breakdown of income & expenditure. Presented at monthly committee mtgs | Judy Godfrey | Monthly Report Produced | Finance | Breakdown of income & expenditure. Presented at monthly committee mtgs | Hall Committee | Monthly Report Produced

## 2018-19
James Hargreaves Hall 3 year Development Plan Last Updated: 10.10.18
|  | 2018 |  |  |  | 2019
|  |  | Activity | Responsible group/person | Completed |  | Activity | Responsible group/person | Completed
General Maintenance | General | Exterior | Review Exterior Refurbishment needs | Hall Committee | Completed | Exterior | Review Exterior Refurbishment needs | Hall Committee | Due March 2019
|  |  | Maintain Gravel Parking Area & Maintenance of Graveyard | Karen Southcott Judy Godfrey Phyllis Diment | Ongoing |  | Maintain Gravel Parking Area & Maintenance of Graveyard | Karen Southcott Judy Godfrey Phyllis Diment | Ongoing
| Maintenance | Interior | Floor Maintenance: Carried out as part of cleaning rota | Cleaning Team Judy Godfrey | Ongoing | Interior | Floor Maintenance: requires sanding & polishing this year | Cleaning Team Judy Godfrey | Due August 2019
Building works | Building works | Exterior |  |  |  | Exterior
|  | Interior | Review Interior Paint Renovations | Hall Committee | Completed | Interior | Review Interior Paint Renovations | Hall Committee | Due August 2019
Health & Safety | Health & |  | Review storage Requirements | Hall Committee | Ongoing |  | Review storage Requirements | Hall Committee | Ongoing
| Safety |  | Carry out annual risk assessments, including disability | Karen Southcott | Completed Oct 2018 |  | Carry out annual risk assessments, including disability | Karen Southcott | Due Oct 2019
|  | Health & Safety | Annual Fire Risk Assessment | Karen Southcott | Completed Oct 2018 | Health & Safety | Annual Fire Risk Assessment | Karen Southcott | Due Oct 2019
|  |  | Ensure annual electrical tests are carried out | Judy Godfrey | Completed Oct 2018 |  | Ensure annual electrical tests are carried out | Judy Godfrey | Due Oct 2019
Support for disabled | Support for disabled | Support for disabled | Annual evaluation of disability access risks | Karen Southcott | Completed Oct 2018 | Support for disabled | Annual evaluation of disability access risks | Karen Southcott | Due Oct 2019
User groups
Committee | Committee |  | Continue to review committee requirements & recruitment when necessary. | Hall Committee | Completed Feb 2018 |  | Continue to review committee requirements & recruitment when necessary. | Hall Committee | Due Feb 2019
|  | Committee | Maintain & Improve Hall Website | Karen Southcott | Ongoing | Committee | Maintain & Improve Hall Website | Karen Southcott | Ongoing
|  |  | Review "Mission" & "Value Add" Statements. Are they still valid? | Hall Committee | Completed Nov 2018 |  | Review "Mission" & "Value Add" Statements. Are they still valid? | Hall Committee | Due Nov 2019
|  |  | Distribute Welcome Pack for people moving to the village | Judy Godfrey | Ongoing |  | Distribute Welcome Pack for people moving to the village | Judy Godfrey | Ongoing
Events | Events | Community Activities/ Support | Review & Revise Welcome Pack for new arrivals when necessary. Review activities, frequency & ages of clubs/events | Hall Committee | Ongoing | Community Activities/ Support | Review & Revise Welcome Pack for new arrivals when necessary. Review activities, frequency & ages of clubs/events | Hall Committee | Ongoing
|  | Fund Raising | Develop new events in order to raise funds | Hall Committee | Ongoing at Committee Meetings | Fund Raising | Develop new events in order to raise funds | Hall Committee | Ongoing at Committee Meetings
Finance | Finance | Finance | Breakdown of income & expenditure. Presented at monthly committee mtgs | Treasurer: Avril Sherring & Hall Committee | Monthly Report Presented | Finance | Breakdown of income & expenditure. Presented at monthly committee mtgs | Treasurer: Avril Sherring & Hall Committee | Monthly Report To Be Presented

## 2019
James Hargreaves Hall 3 year Development Plan Last Updated: 15.10.17
| 2016 |  |  |  |  | 2017 |  |  |  | 2018
|  | Activity | Responsible group/person | Completed |  |  | Activity | Responsible group/person | Completed |  | Activity | Responsible group/person | Completed
General Maintenance | Exterior | Re-Paint shed | Karen Southcott | Completed May 2016 | General | Exterior | Maintenance of Arch Window Management of Condensation Issue | Hall Committee | Ongoing | Exterior | Review Exterior Refurbishment needs | Hall Committee | Discuss Jan 2018
|  | Order & Lay New Gravel for Parking Area & Maintenance of Graveyard | Karen Southcott Judy Godfrey Phyllis Diment | Completed Aug 2016 |  |  | Maintain Gravel Parking Area & Maintenance of Graveyard | Karen Southcott Judy Godfrey Phyllis Diment | Ongoing |  | Maintain Gravel Parking Area & Maintenance of Graveyard | Karen Southcott Judy Godfrey Phyllis Diment | Ongoing
| Interior | Floor Maintenance: Sanded & Polished Every 2 years | Cleaning Team Judy Godfrey | Completed Aug 2015 | Maintenance | Interior | Floor Maintenance: requires sanding & polishing this year | Cleaning Team Judy Godfrey | Completed Aug 2017 | Interior | Floor Maintenance: Carried out as part of cleaning rota | Cleaning Team Judy Godfrey | Ongoing
Building works | Exterior | Remedial work to Rear Steps and Boundary Wall | Hall Committee | Completed Aug 2015 | Building works | Exterior | Review Exterior Paintwork, repaint posts and fence | Hall Committee | Completed Aug 2017 | Exterior
| Interior | Review Interior Paint Renovations | Hall Committee | Reviewed July 2016 |  | Interior | Review Interior Paint Renovations Paint Renovations to the toilet | Hall Committee Karen Southcott | Completed Aug 2017 | Interior | Review Interior Paint Renovations | Hall Committee | Due Aug 2019
Health & Safety |  | Review storage Requirements & Tidy Loft | Hall Committee | Completed Aug 2015 | Health & |  | Review storage Requirements | Hall Committee | Due Nov 2017 |  | Review storage Requirements | Hall Committee | Ongoing
|  | Carry out annual H&S risk assessments | Karen Southcott | Completed Nov 2016 | Safety |  | Carry out annual H&S risk assessments | Karen Southcott | Completed Oct 2017 |  | Carry out annual risk assessments, including disability | Hall Committee | Due Oct 2018
|  | Annual Fire Risk Assessment | Karen Southcott | Completed Oct 2016 |  | Health & Safety | Annual Fire Risk Assessment | Karen Southcott | Completed Oct 2017 | Health & Safety | Annual Fire Risk Assessment | Karen Southcott | Due Oct 2018
|  | Ensure electrical tests are carried out - due in 2 years time | Judy Godfrey | Completed Oct 2015 |  |  | Ensure electrical tests are carried out-due Oct 2017 | Judy Godfrey | Due Oct 2017 |  | Ensure annual electrical tests are carried out | Judy Godfrey | Due Oct 2018
Support for disabled |  | Review Disability Access Risk Assessment/Questionnaire | Karen Southcott | Completed Oct 2016 | Support for disabled | Support for disabled | Annual evaluation of disability access risks | Karen Southcott | Completed Oct 2017 | Support for disabled | Annual evaluation of disability access risks | Karen Southcott | Due Oct 2018
User groups |  | Review user groups . Build up profile of coverage and attendance. Survey/questionaire to ascertain needs | Hall Committee | Ongoing | User groups | User groups | Review user groups . Build up profile of coverage and attendance. Survey/questionaire to ascertain needs | Hall Committee | Ongoing | User Groups | Use information to target future use. | Hall Committee | Ongoing
Committee |  | Review committee Structure. Produce Committee Responsibility List | Hall Committee | Revised Nov 2016 | Committee |  | Review committee Structure. Review Hall Governing Body Document | Hall Committee | Due Nov 2017 |  | Continue to review committee requirements & recruitment when necessary. | Hall Committee | Due Feb 2018
|  | Maintain & Improve Hall Website | Karen Southcott | Ongoing |  | Committee | Maintain & Improve Hall Website | Karen Southcott | Ongoing | Committee | Maintain & Improve Hall Website | Karen Southcott | Ongoing
|  | Review "Mission" & "Value Add" Statements. Are they still valid? | Hall Committee | Reviewed Nov 2016 |  |  | Review "Mission" & "Value Add" Statements. Are they still valid? | Hall Committee | Due Nov 2017 |  | Review "Mission" & "Value Add" Statements. Are they still valid? | Hall Committee | Due Nov 2018
|  | Distribute Welcome Pack for people moving to the village | Judy Godfrey | Ongoing |  |  | Distribute Welcome Pack for people moving to the village | Judy Godfrey | Ongoing |  | Distribute Welcome Pack for people moving to the village | Judy Godfrey | Ongoing
Events | Community Activities/ Support | Review hall hiring documentation. Review range of activities & ages. Discuss gaps & how to fill them. | Hall Committee | Ongoing | Events | Community Activities/ Support | Review hall hiring documentation. Review range of activities & ages. Discuss gaps & how to fill them. | Hall Committee | Ongoing | Community Activities/ Support | Review & Revise Welcome Pack for new arrivals when necessary. Review activities, frequency & ages of clubs/events | Hall Committee | Ongoing
| Fund Raising | Review fund raising activities for year and implement changes. | Hall Committee | Ongoing at Committee Meetings |  | Fund Raising | Review fund raising activities for year and implement changes. | Hall Committee | Ongoing | Fund Raising | Develop new events in order to raise funds | Hall Committee | Ongoing at Committee Meetings
Finance |  | Breakdown of income & expenditure. Presented at monthly committee mtgs | Judy Godfrey | Monthly Report Produced | Finance | Finance | Breakdown of income & expenditure. Presented at monthly committee mtgs | Judy Godfrey | Monthly Report Produced | Finance | Breakdown of income & expenditure. Presented at monthly committee mtgs | Hall Committee | Monthly Report Produced